## Sheet1
Priority	Description	Status	Time	Notes
30	Add monthly balance	1-TODO
30	Confirm when deleting something	1-TODO
40	Proper error handling (wrong/missing id,...)	1-TODO
40	Refactoring DB access	1-TODO
50	Create backup script	1-TODO
80	Integrate 'utils' files into corresponding preparers	1-TODO
100	Translations in a separate file	1-TODO
10	Transition to Smarty	2-DONE	24.12.13 13:13
20	Add book entries	2-DONE	25.12.13 01:02
20	Add default user ('gemeinsam') to book when creating it	2-DONE	24.12.13 15:31
20	Add users to book	2-DONE	25.12.13 00:17
20	Create users in model	2-DONE	24.12.13 13:14
20	Edit a book	2-DONE	25.12.13 00:17
20	Save a new book	2-DONE	24.12.13 23:29
20	User login	2-DONE	25.12.13 20:32
30	Date is stored in a wrong format!	2-DONE	25.12.13 20:11
30	List book entries	2-DONE	25.12.13 01:02
30	Validate that input amount is a float	2-DONE	25.12.13 20:11
40	Display most recent descriptions as suggestion	2-DONE	26.12.13 08:05
40	Sort book entries by date	2-DONE	25.12.13 21:30
50	Nicely formatted input forms (editbook, edituser)	2-DONE	27.12.13 12:00
60	Create special CSS for mobile devices	2-DONE	27.12.13 12:00